## Prep Checklist
Pints & Properties Checklist
30-Days
| Establish date & time | Second Saturday of every month, 3:30pm works for us. Pick a date/time most people can attend, establish a reccuring date/time each month so people can plan well in advance.
| Book venue | Beer availability is a must (ahem, "Pints"), quiet area you can reserve, centrally located, recon in person
| Book guest speaker | See "Guest Speaker" tab for the first year of ideas… speaker talks for 45 mins MAX
| Create event &/or post on social media | See "Logo" tab. Post on Facebook, Instagram, LinkedIn, BiggerPockets, Google my business, etc. Include info on guest speaker & topic
| Build your base of attendees | Go to every Real Estate meetup 30 days prior to your event… make friends, invite them to Pints & Properties
1-Week
| Email invite | Mailchimp, free plan
| Prep "Go Bag" | See "Go Bag" tab. Test / charge all equipment.
| Refresh event &/or media post | Ask friends to share & invite everyone they know
Check in with venue
| Check in with guest speaker | Ask if they'll need a projector / collect slides, offer to print handouts, ask if there's anything you can provide
1-Day
Refresh event &/or media post
Send out another email invite
Check in with venue
| Check in with guest speaker | Tell them to get there 15 minutes early
Day-Of
| Show up early! | Bring "Go-Bag," ensure seating makes sense; move stuff around if necessary
| Hang "Pints & Properties" signs | Front door, outside door to reserved area
| Brief staff | Quiet, turn down music, direct stragglers
| Set up equipment | Projector, mic (if necessary)
| Establish sign-in area | Enforce sign-in & name-tags
Offer to buy speaker a drink
Event
| Small group vs. Large group | Round robin introductions, goals, experience vs. Emphasize sign-in sheet, phones on silent
| Announcements + Introduce guest speaker | Be brief
| Summary | Thank guest speaker, **take a group photo prior to releasing audience's attention,** invite everyone to hang out and network
Post-Event, 72hrs
| Post | Thank guest speaker, share their contact info, slides (if they approve); post group picture… be FUN, not stuffy. Tag everyone.
| Important sign-in list to database | Maintaining a database is critical… these people are your future partners, clients, vendors, friends
| Email | Thanks for coming, share slides, see you next month!
Remember…you set the stage. Your vibes = the meetup's vibes. We are chill, fun & approachable… yet motivated AF. OK?? :) Cool, now go crush it.

## Go Bag
Go Bag Items
| "Pints & Properties" laminated door signs (x2) | https://www.teepublic.com/poster-and-art/8602853-pints-and-properties-logo
| Sign-in sheet | Digital preferred so you can import into mailchimp
| Tape | To hang door signs
| Dry erase marker | To write instructions on door signs, if applicable
| Name tags | Basic, peel & stick - consider color coding per industry type. Ex., Wholesalers = red, Agents = green, Vendors = yellow, etc.
| Sharpies x2 | For name tags
Business cards
Mic set (charged)
Camera (charged)
Projector + stand + screen
| Computer (charged) | If you're using power point slides
Extension Cord
| Apparel | Optional… we have T-shirts & koozies on hand to sell or give out

## Guest Speaker
Speakers
1 | Attorney 1 | Subject-To, wholesale deals, auction properties
2 | Attorney 2 | What an attorney actually does/timeline, LLC setup pros/cons, common mistakes/misunderstandings
3 | Lender 1 | Delayed financing
4 | Lender 2 | Primary residence loans to house hack + rehab loans (VA Reno, FHA 203K)
5 | Local bank | Lines of Credit, interesting loan products
6 | Inspector | What's truly concerning, what's no biggie
7 | Contractor | How to quickly estimate repairs
8 | Flipper | Tips
9 | Wholesaler | How to find off-market deals
10 | Appraiser | What to do to get the most value on BRRRRs and flips
11 | TSP Specialist | How to invest in real estate using your TSP
12 | How to run numbers | Market-specific, using a BP calculator
**Out of ideas? The Pillars are always down to be guest speakers!

## Logo
PINTS & PROPERTIES
Pints & Properties is a real estate investors meetup to collaborate over beers, share knowledge, and network with like-minded people.
We bring in community members who are crushing it to speak on topics ranging from deal strategy, creative financing, how to build your team and where to find off-market properties.
We meet at rotating breweries on the second Saturday of every month at 3:30pm. Stay tuned to our Facebook group for changes or updates!